## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | DONE
1 | A User Should be able to choose to create a profile either as a member or as an organization | 1 | Sohail |  |  | 1
1.1 | A User Should be able to create a profile as a member | 2 | Sohail |  |  | 1
1.2 | A Member Should be able to view his profile | 2 | Sohail |  |  | 1
1.3 | A Member Should be able to edit his profile | 3 | Sohail
1.4 | A Member Should be able to delete his profile | 3 | Sohail
1.5 | A Member's Profile Should be visible to other users | 2 | Sohail
1.6 | A User Should be able to create a profile as a Partner Organization | 1 | Basem |  |  | 1
1.7 | A Partner Should be able to View their Profile | 2 | Basem |  |  | 1
1.8 | A Partner Should be able to edit their Profile | 3 | Basem |  |  | 1
1.9 | A Parnter Should be able to delete his profile | 3 | Basem |  |  | 1
2 | A Partner's Profile Should be visible to other users | 2 | Basem |  |  | 1
2.1 | A User Should be able to create a profile as a Consultancy Organization | 1 | Hossam |  |  | 1
2.2 | A Consultanct Should be able to View their Profile | 2 | Hossam |  |  | 1
2.3 | A Consultanct Should be able to edit their Profile | 3 | Hossam |  |  | 1
2.4 | A Consultanct Should be able to delete his profile | 3 | Hossam |  |  | 1
2.5 | A Consultanct's Profile Should be visible to other users | 2 | Hossam |  |  | 1
2.6 | A User Should be able to create a profile as an Educational Organization | 1 | Gaafar |  |  | 1
2.7 | An Educational Organization Should be able to View their Profile | 2 | Gaafar |  |  | 1
2.8 | An Educational Organization Should be able to edit their Profile | 3 | Gaafar |  |  | 1
2.9 | An Educational Organization Should be able to delete his profile | 3 | Gaafar |  |  | 1
3 | An Educational Organization's Profile Should be visible to other users | 2 | Gaafar |  |  | 1
3.1 | A Member Should be able to View Masterclasses | 1 | Moataz
3.2 | A Member Should be able to require assesment with an Expert | 3 | Moataz
3.3 | A Member should be notified if his request is accepted | 3 | Moataz | 3.6 | Test Integration
3.4 | A Member Should be able to apply for a masterclass | 2 | Moataz
3.5 | A Member Should be able to View Recommended Masterclasses | 5 | Moataz | 3.7 | Test Integration
3.6 | An Expert Should be able to Respond to requests by members | 3 | Mahmoud | 3.2 | Test Integration
3.7 | An Expert Should be able to Assess Members | 2 | Mahmoud
3.8 | A Partner Should be able to Submit an Application of a Task | 2 | Mahmoud |  |  | 1
3.9 | A Partner Should be able to Edit His Submitted Application as long as it hasn't been reviewed | 3 | Mahmoud | 4.2 | Test Integration
4 | A Partner Should be able to Negotiate over his Application | 5 | Mahmoud |  |  | 1
4.1 | An Admin Should be able to View Applications | 1 | Youssef
4.2 | An Admin Should be able to review an Application | 2 | Youssef
4.3 | An Admin Should be able to Respond to Consultant Applications | 3 | Youssef
4.4 | An Admin Should be able to negotiate over an Application | 5 | Youssef
4.5 | A Consultant Should be able to view Applications | 1 | Youssef |  |  | 1
4.6 | A Consultant Should be able to apply for Applications | 2 | Youssef |  |  | 1
4.7 | Tasks Should be visible to Users | 1 | Karim
4.8 | A Member should be able to view his recommended tasks | 5 | Karim
4.9 | A Member Should be able to Apply for a Task | 2 | Karim
5 | A Member Should be able to delete his application for a Task | 3 | Karim
5.1 | A Partner Should be able to Post a Task if he chose to proceed without consultancy | 2 | Karim
5.2 | A Partner Should be able to respond to requests if he chose to proceed without consultanct | 3 | Karim
5.3 | An Admin Should be able to review Tasks | 1 | Kashlan
5.4 | An Admin Should be able to add extra attributes to a Task | 2 | Kashlan
5.5 | An Admin Should be able to edit a Task | 3 | Kashlan
5.6 | An Admin Should be able to delete a Task | 3 | Kashlan
5.7 | A Consultant Should be able to Respond to Member Applications for a Task | 2 | Kashlan | 4.9 | Test Integration
5.8 | A Consultant should be able to post a Task | 2 | Kashlan
5.9 | An Application Should be identified with a set of attributes | 2 | Youssef
6 | A Task Should be identified with a set of attributes | 2 | Moataz
6.1 | A User should be identified with a set of attributes | 2 | Mahmoud
6.2 | A Member should be identified with a set of attributes | 2 | Karim
6.3 | A Partner Should be identified with a set of attributes | 2 | Kashlan
6.4 | A Consultant Should be identified with a set of attributes | 2 | Gaafar
6.5 | A Masterclass Should be identified with a set of attributes | 2 | Sohail
6.6 | An Educational Organization Should be identified with a set of attributes | 2 | Basem